# Event Production & AV Requirements Brief

Northstar Leadership Summit 2026

Reference: NLS-2026-RFP-01  |  Status: Planning brief  |  Confidentiality: Demo only

# Event overview

| Client organization | Northstar Health Collaborative |
| --- | --- |
| Event name | Northstar Leadership Summit 2026 |
| Event type | Annual corporate leadership conference |
| Event format | In-person with a live virtual audience for the general sessions |
| Location | Chicago, Illinois |
| Venue | Lakeside Grand Chicago |
| Event dates | September 14–16, 2026 |
| Expected attendance | 450 in person; up to 300 concurrent virtual viewers |
| Primary contact | Jordan Lee, Events Director — jordan.lee@example.com |
| Proposal due | August 7, 2026 at 5:00 p.m. Central Time |
| Planning budget | USD 180,000–240,000 for event production and AV services |

# Objectives and audience

The summit will bring together Northstar executives, regional directors, clinical leaders, and invited partners. The experience should feel confident, modern, and highly polished while remaining accessible to both in-room and remote participants.

Deliver a high-energy opening general session and an executive strategy program.

Support clear communication across one ballroom and three concurrent breakout rooms.

Provide a dependable broadcast-quality stream for remote viewers.

Capture approved sessions for internal on-demand viewing after the event.

Maintain an uncluttered scenic design using Northstar’s navy, teal, and white brand palette.

# Program schedule

| Date | Operating hours | Program | Rooms |
| --- | --- | --- | --- |
| Sep 13 | 1:00–8:00 p.m. | Vendor load-in, build, testing | Grand Ballroom + breakouts |
| Sep 14 | 7:00 a.m.–7:00 p.m. | Opening, keynotes, breakouts, reception | Ballroom + 3 breakouts |
| Sep 15 | 7:00 a.m.–6:00 p.m. | General session and concurrent breakouts | Ballroom + 3 breakouts |
| Sep 16 | 7:00 a.m.–3:00 p.m. | Closing sessions; strike begins at 3:30 p.m. | Ballroom + 2 breakouts |

# Production scope

## Grand Ballroom

General-session seating for 450 with clear sightlines and accessible aisles.

16:9 center presentation screen, confidence monitors, branded stage wash, and IMAG.

Four-camera production: two operated cameras, one locked wide camera, and one confidence/utility camera.

Digital audio console, lectern microphone, six wireless lavaliers, four wireless handheld microphones, playback, and recording feeds.

Show caller, technical director, audio engineer, video engineer, graphics operator, camera operators, stage manager, and utility support.

Live captions displayed in-room and embedded in the virtual program.

## Breakout rooms

Three concurrent rooms on September 14 and 15; two rooms on September 16.

Each room requires presentation display, laptop connectivity, audio reinforcement, one wireless lavalier, one handheld microphone, and a technician.

Room A requires a remote presenter contribution and return confidence monitor.

Sessions in Room A should be recorded; recording for Rooms B and C remains optional pending cost review.

## Streaming, recording, and content

Stream general sessions to a browser-based platform for up to 300 concurrent viewers.

Include branded holding slides, lower thirds, speaker names, agenda slates, and moderated Q&A.

Record program and clean feeds in 1080p; provide edited keynote files within five business days.

Client will provide final presentation files by September 9, 2026.

# Vendor response requirements

Provide an itemized equipment, labor, travel, service-charge, and tax breakdown.

State all assumptions, exclusions, overtime rules, minimum calls, cancellation terms, and change-order procedures.

Identify the proposed project lead and department leads.

Provide proof of insurance and two examples of comparable corporate events.

Offer a base solution plus clearly labeled options for breakout recording and enhanced scenic treatment.

# Items to confirm during planning

The client has not yet selected the streaming platform, confirmed the final scenic package, or decided whether Rooms B and C require recording. Vendors should identify recommended choices and the associated investment impact.